| Five- Year Strategic Plan 2022-2027 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A.T. Still University Speech-Language Pathology Graduate Program |  |  |  |  |  |  |  |
| Focus Areas | Goal | Strategy/Project | Action Plan | Indicators of Success (KPI) | Responsible Party | Budget Consideration | Timeline |
| Student Enrollment | Increase # of Admitted Students | Recruitment |  | Meet the target number |  |  |  |
|  | 30 | Recruit and enroll at least 4 students from culturally/linguistically diverse groups | ASHA Convention Booth ‘21/ Social Media/ Mailing UG programs SLP/ Virtual Sessions | 30 | Program Director (PD) Communication and Marketing | Proforma | 2022-2023 |
|  | 35 | Recruit and enroll at least 8 students from culturally/linguistically diverse groups | ASHA Booth ‘22/Social Medial/Mailing UG programs SLP/Virtual Sessions | 35 | Program Director (PD) Communication and Marketing | Proforma | 2023-2024 |
|  | 40 | Recruit and enroll at least 12 students from culturally/linguistically diverse groups | ASHA Booth ‘23/Social Media/Mailing UG programs SLP/Virtual Sessions | 40 | Program Director (PD) Communication and Marketing | Proforma | 2024-2025 |
|  | 45 | Recruit and enroll at least 13 students from culturally/linguistically diverse groups | ASHA Booth ‘24/Social Media/Mailing UG programs SLP/ Virtual Sessions | 45 | Program Director (PD) Communication and Marketing | Proforma | 2025-2026 |
|  | 50 | Recruit and enroll at least 14 students from culturally/linguistically diverse groups | ASHA Booth ‘25/Social Media/Mailing UG programs SLP/Virtual Sessions | 50 | Program Director (PD) Communication and Marketing | Proforma | 2026-2027 |
|  | Graduation of students within the program in a timely manner | Provide student supports to increase student graduation rate and decrease student attrition | Review student academic status at Student Disposition Reviews, Provide student remediation as needed | 95%-100% | Program Director/ Faculty/ Students | Two years | 2024 (30) 2025 (35) 2025 (40) 2026 (45) 2027 (50) |
| Faculty Growth | Increase # of Faculty | Recruitment |  | Meet the target number |  |  |  |
|  | (2) Program Director/ Clinic Director | Recruit at least one faculty from a culturally/linguistically diverse background | Search Committee | 2 | Interim Program Director Vice Dean | Salaries Proforma | 2020-2021 |
|  | (3) 2 doctoral degree 1 master degree | Recruit at least two faculty from culturally/linguistically diverse backgrounds | Search Committee | 3 | Program Director/Search Committee | Salaries Proforma | 2022-2023 |
|  | (3) 1 master 2 doctoral | Recruit at least one faculty from a culturally/linguistically diverse background | Search Committee | 3 | Program Director/Search Committee | Salaries Proforma | 2023-2024 |
|  | 1 doctoral | Recruit at least one faculty from a culturally/linguistically diverse background | Search Committee | 1 | Program Director/Search Committee | Salaries Proforma | 2024-2025 |
|  | 1 doctoral | Recruit faculty from culturally/linguistically diverse background | Search Committee | 1 | Program Director/Search Committee | Salaries Proforma | 2025-2026 |
| Academic Excellence | Technological Advancement: Students will be competent in the use of instrumentation | Laboratory Training | FEES Stroboscopy Endoscopy VisiPitch Aerophone Telehealth technology | One experience per student in each instrument | Faculty members | $200,000 proforma | Once in Spring I or Fall II for each cohort over 5 years |
|  | Research Productivity: Students will complete and present one research study | Carry out research study with support of faculty member in research course | 1) Identify problem, 2) gather data, 3) analyze data, 4) write paper, 5) present findings in ProSemand/or external venue | All students complete five points of action plan | Faculty members | Consideration of student monetary support if research paper is accepted for conference presentation | Fall I for each cohort over 5 years |
| Diversity | Clinical service with culturally and linguistically diverse (CLD) populations | Clinical placement in (CLD) site | Students will have at least one CLD client in school or medical setting | Each student has at least one CLD site with one CLD patient | Director of Clinical Education/Clinical Educator | Clinical Educator payment as needed | During two-year graduate program |
|  | Clinical service with culturally and linguistically diverse (CLD) populations | Experience with an interpreter | Students will have experience in real time or designed scenarios | Each student will have at least one interpreter experience | Faculty member/Clinical Educator | Clinical Educator payment as needed | During two-year graduate program |
| International Efforts | Clinical service with international populations | Experience at least one treatment or intervention experience with international population | Students will have an international experience onsite in another country or through telepractice | Each student will complete one international clinical experience | DCE/Faculty | Support for international experience through Rotaplast Scholarship or School support | During two-year graduate program |
| IPE/IPP | Engage in IPE | IPE student experience through ATSU | Engage in case-based ATSU IPE experience | All students complete the case | ATSU IPE Program Director/Student Advisor | - | Year 1 |
|  | Engage in IPE | IPE capstone | Complete IPE in SPCH 5420 and SPCH 5440 courses | All students complete the IPE project | Course Faculty/ASHS Faculty | - | Year 1 Spring Session 2 |
| Program Support | Develop Program Advisory Board | Build advisory board and board goals | Identify 2-3 board members over 4 years for a total of 8-10 board members Prepare Board Strategic Plan and Goals | Board members meet and develop board strategic plan in year one, board yearly goals each year, meet twice yearly | Program Director | Dinner for Advisory Meeting | 2022-2023 2023-2024 2024-2025 2025-2026 |
| Student Success | Students will Receive academic/ service/ leadership awards | Review ASHA/NSSLHA scholarship calls each July / ATSU GPS Scholars | Support students to apply for Minority Student Leadership Program | Receive at least one award by year 3 of program | Program Director/Advisor | Support for travel to conference to accept awards | Yearly |
|  |  |  | Apply for other ASHA Awards and also other opportunities | Receive at least one award every two years | Program Director/Advisor | Support for travel to conference to accept awards | Yearly |
|  | Students will participate in community service/service learning | Identify community service opportunities e.g. OT/PT probono clinic, Matter of Balance, E.A.R. Day, Community dental event with CARE Partnership, ASHS Rebuilding Together, SOMA Nutrition & health awareness, Special Olympics, ATSU Day for Special Smiles, AZ Camp Sunrise | Student will present opportunities to advisor for approval | Complete 10 hours | Student/Advisor | - | Two-years |
| Faculty Success | A faculty member will receive teaching/ service/ research/ leadership awards | Identify awards available | Apply for awards | One award every other year | Program Director/Faculty Members | Support to travel to receive award | BiYearly |
|  | Faculty will receive tenure | Prepare 3-year review Portfolio | Review portfolio | Positive Review | Program Director/Faculty | - |  |
|  | “ | “ | - 2 faculty hired in 2021 | 3 faculty will complete promotion and tenure 3-year reviews | 2 faculty | - | 2024-2025 4th year |
|  | “ | “ | - 3 faculty hired in 2022 | - | 3 faculty | - | 2025-2026 4th year |
|  | “ | “ | - 3 faculty hired in 2023 | - | 3 faculty | - | 2025-2026 4th year |
|  | Faculty will receive promotion | Prepare 3-year Review Portfolio | Review portfolio | Positive Review | Program Director/Faculty | - |  |
|  | “ | “ | - 2 faculty hired in 2021 | - | 2 faculty | - | 2024-2025 4th year |
|  | “ | “ | - 3 faculty hired in 2022 | - | 3 faculty | - | 2025-2026 4th year |
|  | “ | “ | - 3 faculty hired in 2023 | - | 3 faculty | - | 2025-2026 4th year |
|  | Faculty will present papers/ workshops of research/clinical cases | Identify opportunities | Apply for awards | At least 50% of faculty presenting | Faculty | Support to travel for presentation | Yearly |
|  | Faculty will submit research for publication | Identify research projects and complete | Submit research proposal | At least 50% of faculty submit | Faculty | - | Yearly |
|  | Faculty will publish research | Identify journals for submissions | Review of submitted proposal | 2-3 articles in department | Faculty | - | Yearly |
|  | Faculty will receive grants | Identify grant opportunities | Submit grant proposal | 1 grant yearly at least 4 grants in 5 years | Faculty | - | Yearly |
|  | Faculty will participate in community service/service learning | Identify community service opportunities e.g. OT/PT pro bono clinic, Matter of Balance, E.A.R. Day, Community dental event with CARE Partnership, ASHS Rebuilding Together, SOMA Nutrition & health awareness, Special Olympics, ATSU Day for Special Smiles, AZ Camp Sunrise | Regular participation with students | Focused involvement associated with academic/ clinical education | Faculty | - | Yearly |